## PM
Autonomous Mobile Robots using Cloud Services
Student:		Bruno Kroller
Project Director:		Juan Antonio Breña Moral

ID	PHASE	AREA	TASK	INIT	FINISH	COMMENTS
	INCEPTION		Define the task included in inception phase	01/09/11	01/11/11
	ELABORATION		Define the task included in elaboration phase	01/09/11	01/11/11
	CONSTRUCTION	INFRAESTRUCTURE	Install Ubuntu 10.04	01/09/11	01/10/11
	CONSTRUCTION	INFRAESTRUCTURE	Install LeJOS 0.9	01/09/11	01/10/11
	CONSTRUCTION	INFRAESTRUCTURE	Test LeJOS Tools	01/09/11	01/10/11	Milestone
	CONSTRUCTION	NXT	Build a NXT robot	01/09/11	15/10/2011
	CONSTRUCTION	LEJOS	Unit tests: Program to read GPS data	01/10/11	15/10/2011
	CONSTRUCTION	LEJOS	Video
	CONSTRUCTION	LEJOS	Unit tests: Test program during 1 day and save a kml file	01/10/11	15/10/2011
	CONSTRUCTION	LEJOS	Unit tests: Develop a program to avoid obstacles	01/10/11	15/10/2011
	CONSTRUCTION	LEJOS	Video
	CONSTRUCTION	LEJOS	Unit tests: Develop a way to follow 2 GPS points	01/10/11	01/11/11
	CONSTRUCTION	LEJOS	Unit tests: Test navigation program yourself	01/11/11	01/12/11
	CONSTRUCTION	LEJOS	Video
	CONSTRUCTION	LEJOS	Integrate: GPS, Obstacle navigation and waypoint navigation	01/12/11	01/02/12	Milestone
	CONSTRUCTION	LEJOS	Debug software with PC using Rconsole	01/01/11	01/02/12
	CONSTRUCTION	ANDROID	Connect NXT with Android	01/02/12	01/04/12
	CONSTRUCTION	ANDROID	Unit Tests: Connect NXT with Android	01/02/12	01/04/12
	CONSTRUCTION	ANDROID	Unit Tests: Send data from NXT to Android and Android to NXT	01/02/12	01/04/12
	CONSTRUCTION	ANDROID	Video
	CONSTRUCTION	ANDROID	Integrate Android with NXT	01/02/12	01/04/12	Milestone
	CONSTRUCTION	APP ENGINE	Unit Tests: Deploy your first application	01/04/12	01/06/12
	CONSTRUCTION	APP ENGINE	Unit Tests: Create a WS	01/04/12	01/06/12
	CONSTRUCTION	APP ENGINE	Unit Tests: Show a coordinate in a Google Map	01/04/12	01/06/12
	CONSTRUCTION	APP ENGINE	Unit Tests: Send data from Android to WS	01/04/12	01/06/12
	CONSTRUCTION	APP ENGINE	Integrate Android to WS	01/04/12	01/06/12	Milestone
	CONSTRUCTION	APP ENGINE	Video

## BRUNO
Pruebas Unitarias

1	Instalación de equipo con Ubuntu
2	Instalacion de eclipse + Java
3	conexión bluetooth via PC
4	conexión bluetooth via NXT
5	lectura de GPS via NXT

## OCTUBRE2011
Gestión de tareas Octubre 2011

ID	TAREA	INICIO	FIN	FINALIZADO	COMENTARIOS
1	INSTALACION UBUNTU	02/10/11	17/11/2011	SI
2	INSTALACION JAVA	02/10/11	17/11/2011	SI
3	INSTALACION LEJOS	02/10/11	17/11/2011	SI
4	INSTALACION ECLIPSE	02/10/11	17/11/2011	SI
5	INSTALACION LEJOS PLUGIN ECLIPSE	02/10/11	17/11/2011	SI
6	PRUEBAS INICIALES	02/10/11	09/10/11
7	CONEXION BLUETOOTH GPS	02/10/11	09/10/11
8	PARSEO GPS	02/10/11	09/10/11
9	USO DE CLASE COORDINATES	02/10/11	09/10/11
10	CALCULO DE DISTANCIAS	02/10/11	09/10/11
11	PRUEBA DE NAVEGACION PRELIMINAR	02/10/11	09/10/11

## NOVIEMBRE2011
Gestión de tareas Octubre 2011

ID	TAREA	INICIO	FIN	FINALIZADO	COMENTARIOS
1	INSTALACION UBUNTU	02/10/11	17/11/2011	SI	Tiene una version 64bits. La instalacion de bluetooth nativa no le va
2	INSTALACION JAVA	02/10/11	17/11/2011	SI
3	INSTALACION LEJOS	02/10/11	17/11/2011	SI	No usó la documentación que use
4	INSTALACION ECLIPSE	02/10/11	17/11/2011	SI
5	INSTALACION LEJOS PLUGIN ECLIPSE	02/10/11	17/11/2011	SI
6	PRUEBAS INICIALES	02/10/11	30/11/2011
7	CONEXION BLUETOOTH GPS	02/10/11	30/11/2011
8	PARSEO GPS	02/10/11	30/11/2011
9	USO DE CLASE COORDINATES	02/10/11	30/11/2011
10	CALCULO DE DISTANCIAS	02/10/11	30/11/2011
11	PRUEBA DE NAVEGACION PRELIMINAR	02/10/11	30/11/2011

Notas:
20/11/2011
Una vez que tienes instalado la infraestructura, es necesario desarrollar:
Una clase que se conecte con un GPS Bluetooth
Una clase que use un objeto de tipo DifferentialPilot